**Project Schedule Plan**

|  |  |  |
| --- | --- | --- |
| Name and Surname: Ryan Cortis | | |
| Date From | Date To | Task |
| 7th April | 25th April | Working on prototype, title Page and basic formatting of documentation |
| 10th April | 26th April | Write the Introduction (Hypothesis, Research Question, Aims, Objectives, Motivation and Relevance of research) |
| 25th April | 26th May | Recording of Prototype video |
| 28th April | 6th May | Write the Research Methodology |
| 7th May | 8th May | Write the Evaluation |
| 9th May | 20nd May | Write the Literature Review |
| 21st May | 24th May | Write the Conclusion, Abstract and Keywords |
| 25th May | 27th May | Write the Dissertation Proposal |
| 27th May | 28th May | Reviewal of documentation and submission |